| Product Backlog Report DataPack Energy Forecaster – CeDInt floor 1 (TBDA) Product: a data product that cleans the CeDInt energy and environmental data, predicts the next 24 hours of energy consumption per zone and load type, and explains which conditions (temperature, humidity, light, occupancy) drive it. Backlog items are grouped by the Week 5 subteams; the ID is the task ID from the sprint plan, with the owner below it. Status on 5 Oct 2026 · 47 items · 33 High, 13 Medium, 1 Low · Sprint 1 = Oct 1–14, 2 = Oct 15–28, 3 = Oct 29–Nov 11, 4 = Nov 12–25 | Status. Not Started. In Progress. Complete. Overdue. On Hold. |  | Priority. High. Medium. Low. |
| --- | --- | --- | --- |

| ID | As a … | I want to … | So that … | Priority | Sprint | Status |
| --- | --- | --- | --- | --- | --- | --- |
| A. Data Engineering · P1 (lead), P2, P3 |  |  |  |  |  |  |
| A1 P1 | Data engineer | load all 18 sheets of the 4 Excel files and save one interim CSV per zone × load type | the team works from fast, identical copies and the raw files stay untouched | High | 1 | In Progress |
| A2 P2 | Data engineer | rename columns to one standard schema, parse timestamps (Europe/Madrid), sort, drop duplicates and add the period label | every later step can rely on the same column names and types | High | 1 | In Progress |
| A3 P3 | Data engineer | resample the 2025 minute data to hourly and align the 2020–23 data to the full hour, without filling gaps | both sampling periods can be compared and modelled together | High | 1 | In Progress |
| A4 P1 + P4 | Forecaster | compute hourly energy_wh from the counter, treating counter = 0 as missing and flagging real resets | the forecast target is not polluted by fake ±100 000 Wh jumps | High | 1 | In Progress |
| A5 P2 | Analyst | have one long table cedint_f1_hourly.csv (hour × zone × load type) with environment columns attached once per zone | I can analyse any series without joining files | High | 1 | In Progress |
| A6 A | Forecaster | get hourly outdoor weather for Montegancedo 2020–2025 from Open-Meteo | HVAC consumption can be explained by the outdoor climate | High | 2 | Not Started |
| A7 A | Forecaster | have a Madrid holiday calendar and an August flag | low-use days are predicted correctly | Medium | 2 | Not Started |
| A8 A | Forecaster | have one feature table (calendar, lags t−1/t−24/t−168, rolling 24 h mean, degree-hours, environment, occupancy) | every model is trained on the same inputs without data leakage | High | 2 | Not Started |
| A9 A | Forecaster | request extra feature variants and get them within the sprint | I can test new ideas quickly | Medium | 3 | Not Started |
| A10 A | Auditor | run the whole pipeline from raw data to features in one notebook | every result can be reproduced | High | 3 | Not Started |
| A11 A | Future user | have a frozen data version v1.0 with clean code and a README | the DataPack can be rerun after the course and released on Moodle | High | 4 | Not Started |
| B. Data Quality & Validation · P4 (lead), P5, P6 |  |  |  |  |  |  |
| B0 | Data analyst | Have the data already merge | I can clean everything in with one code |  |  |  |
| B1 P4 | Building manager | see a map of which hours have data for every series, with coverage % per year and all gaps > 24 h | I know how far I can trust each forecast | High | 1 | In Progress |
| B2 P5 | Analyst | separate stored zeros from real zeros (Temp = Hum = 0, Lum = 0 in daytime, Pres) and set missing values to NaN | a missing reading is not mistaken for 0 °C or a dark room | High | 1 | In Progress |
| B3 P6 | Data quality analyst | classify every counter drop (placeholder zero, short dip, real reset) and every negative-power series (reversed clamp, noise, mixed) | each problem gets the right rule and a flag instead of a wrong correction | High | 1 | In Progress |
| B4 P5 | Analyst | flag physically impossible values (Temp, Hum, power factor) and power spikes above the 99.9th percentile | sensor errors do not distort profiles or models | High | 1 | In Progress |
| B5 P4 + P6 | Auditor | run the consistency checks (power vs energy, apparent vs active, current vs power, environment, periods) with a pass rate per series | physical plausibility is proven, not assumed | High | 1 | In Progress |
| B6 B | Forecaster | have the quality checks re-run on the feature table | no errors are introduced by feature engineering | Medium | 2 | Not Started |
| B7 B | Forecaster | compare model results with and without flagged rows | I know whether our cleaning choices change the conclusions | Medium | 2 | Not Started |
| B8 B | Building manager | see residuals of each model by hour, season and zone | I know when the forecast is less reliable | High | 3 | Not Started |
| B9 B | Facilities technician | get a list of the largest forecast errors as candidate anomalies | I can check unusual days or broken meters | Medium | 3 | Not Started |
| B10 B | Teacher | read a robustness section on what the models get wrong and why | the limits of the forecasts are stated clearly | Medium | 4 | Not Started |
| C. Exploration & Environment · P7 (lead), P8 |  |  |  |  |  |  |
| C1 P7 | Building manager | see average power by hour, weekday and month per zone and load type, split into working days, weekends and August | I understand where and when energy is used | High | 1 | In Progress |
| C2 P8 | Analyst | test whether Pres is occupancy (share by hour/weekday, relation with Lighting and Plugs) | the model uses the right driver | High | 1 | In Progress |
| C3 P8 | Analyst | see time series, distributions and first scatters of Temp, Hum and Lum per zone | I know which relations look linear, U-shaped or absent | Medium | 1 | In Progress |
| C4 P7 | Forecaster | compare 2020–23 with 2025 and flag 2020 as a possible COVID year | abnormal periods do not bias training | Medium | 1 | In Progress |
| C5 C | Building manager | see the full relation matrix (all drivers × all load types) with correlation heatmaps per zone | I know which conditions drive each type of consumption | High | 2 | Not Started |
| C6 C | Analyst | have a lag analysis (0–6 h) and a written interpretation of every relation | delayed effects (e.g. HVAC) and surprises are explained | Medium | 2 | Not Started |
| C7 C + D | Building manager | see SHAP explanations of which drivers matter per load type | I can trust and act on the forecast | High | 3 | Not Started |
| C8 C | Presentation audience | see 3–4 strong key visuals in the final deck | I “see the evidence” at a glance | High | 4 | Not Started |
| D. Modelling & Forecasting · P9 (lead), P10 |  |  |  |  |  |  |
|  | Forecaster | Have clean data | I can build a solid model |  |  |  |
| D1 P9 | Forecaster | have a chronological train/test split and functions for MAE, RMSE, CV(RMSE) and NMBE | every model is compared in the same, fair way | High | 1 | In Progress |
| D2 P10 | Forecaster | build a seasonal-naive and a linear-regression baseline on NW HVAC | every later model has a bar to beat | High | 1 | In Progress |
| D3 P9 + P10 | Team member | have a short model plan (SARIMAX, LightGBM, Prophet) with the features each needs | subteams A and C know what to prepare | Medium | 1 | In Progress |
| D4 D | Building manager | get baseline forecasts for all priority series (HVAC, Lighting, Plugs, total) | I have a first forecast for every important load | High | 2 | Not Started |
| D5 D | Forecaster | fit a SARIMAX model with weather drivers on HVAC | weather-driven seasonality is captured | Medium | 2 | Not Started |
| D6 D | Building manager | get LightGBM day-ahead (24 h) forecasts for all priority series, tuned with TimeSeriesSplit | forecasts are as accurate as possible | High | 3 | Not Started |
| D7 D | Auditor | see the models tested on 2023 and 2025 data they have never seen | the reported performance is honest | High | 3 | Not Started |
| D8 D | Forecaster | try Prophet as an optional extra model | we know whether a third model family adds value | Low | 3 | Not Started |
| D9 D | Institution | get a final model comparison with ASHRAE 14 pass/fail per series | we can prove the forecasts are good enough | High | 4 | Not Started |
| E. Coordination & Communication · P11 (coordinator), P12 |  |  |  |  |  |  |
| E1 P11 | Team member | have the GitHub repo and Drive folders with a README and access for everyone | everybody knows where code, data and documents live | High | 1 | In Progress |
| E2 P12 | Teacher | read a CRISP-DM document (phases 1–3 now, 4–6 later) | a recognised data-mining methodology is visible | High | 1 | In Progress |
| E3 P11 | Auditor | have an experiment log with every model run and its metrics | all experiments and their performance are documented | High | 1 | In Progress |
| E4 P12 | Teacher | see a weekly presentation with team composition, progress per subteam and one finding | I can follow the progress every week | High | 1 | In Progress |
| E5 E | Teacher | see CRISP-DM phases 3–4 written and the experiment log up to date | documentation keeps pace with the work | Medium | 2 | Not Started |
| E6 E + C | Building manager | use a dashboard with consumption, forecast vs actual and drivers | I have one place to monitor and plan energy use | High | 3 | Not Started |
| E7 E | Institution | give a 20-minute final presentation with a speaker split, rehearsed Nov 26–28 | we convince the audience on Nov 30 | High | 4 | Not Started |
| E8 E | Busy stakeholder | get a 2-minute video or one-page summary | I get the message without the full deck | Medium | 4 | Not Started |
| E9 E | Teacher | find code, data dictionary, experiment log, report, deck and dashboard in Moodle by Dec 14 | the project can be graded and audited | High | Post | Not Started |
|  | Client CeDint | Read the results of the model | I Can reduce my consumption | High |  |  |